## Ark1
Lofthus Frukt og Saft
Team: | Project Manager | Copywriter | Visual Designer | Photograph | Front-End Developer
Task | Date start | Days to complete
First meeting with Lofthus | 1 | 1
Planing and deligering | 1 | 1
Visit, gather articles and interview | 2 | 3
Write content | 5 | 5
Take pictures | 2 | 2
Edit pictures | 4 | 2
Make several styletiles | 2 | 2
Meet Lofthus and decide styletile | 4 | 1
Build page with html and CSS | 5 | 3
Add contact form | 8 | 2
Add order page | 8 | 2
Add location | 8 | 2
Meet Lofthus - feedback and adjustment | 10 | 1
Add articles and pictures to the page | 11 | 1
Testing and debugging | 12 | 1
Launching | 13 | 1